## SDD Delivery Tracker
Day | Planned Date | Actual Date | SDD Phase | Activities Performed | Artefacts Produced | Deliverable | Status
1 | Thu 17 Sep 2026 | Thu 17 Sep 2026 | Discovery & Setup | Initialized INT Control Plane, .agent/, .agents/skills/, AGENTS.md, and execution folders. Read INT_SDD_Standard.md. Analysed business requirements, raised and evaluated 61 open questions, 22 assumptions, 14 dependencies, and 13 out-of-scope boundaries. | .ai-context/discovery/employee-internal-transfer.discovery.md; .ai-context/project_context.md; AGENTS.md; .gitignore | D1 | Done
2 | Fri 18 Sep 2026 | Fri 18 Sep 2026 | BRD Customization + Constitution | Authored customized BRD v1.1 (BRD-001 to BRD-006: 3-stage approval, 6-month tenure eligibility, rating >= Meets Expectations, zero PIP, 5-day review SLA, IJP vacancy mapping). Ratified constitution.md v1.0 (Node/Express, React, PostgreSQL, Prisma, JWT, Modular Monolith). Logged all decisions in decision-log.md. | .ai-context/BRD.md; .ai-context/brd-change-log.md; .ai-context/constitution.md; .ai-context/decisions/employee-internal-transfer.decision-log.md | D2 | Done
3 | Sat 19 Sep 2026 | Sat 19 Sep 2026 | Specification + AC + API Contracts | Formulated feature specification with 55 acceptance criteria in Given/When/Then, 9 API contracts with exception payloads and rate limits, 3-tier sequential workflow state machine, and data models. | .ai-context/specs/employee-internal-transfer.spec.md v1.3 | D2 | Done
4 | Mon 21 Sep 2026 | Mon 21 Sep 2026 | Test Cases & Integration Scenarios | Authored 96 acceptance test cases mapped directly to AC IDs, full state-transition matrix, and 10 end-to-end integration scenarios (INT01-INT10) covering happy path, rejection, withdrawal, and downstream partial failure resilience. | .ai-context/test_cases/employee-internal-transfer.test_cases.md; .ai-context/test_cases/_integration.md | D3 | Done
5 | Tue 22 Sep 2026 | Tue 22 Sep 2026 | Gate 0 (BRD) & Gate 1 (Spec Review) | Submitted BRD v1.1 and Feature Spec for formal Gate 0 and Gate 1 PR Reviews by assigned reviewer Supratim Jetty (supratim.jetty@intglobal.com). Verified 11-point review checklist, conditional approvals, and development readiness. | .ai-context/pr_reviews/gate-1-review.md; .ai-context/status.md | D9 | In Progress
6 | Wed 23 Sep 2026 |  | Implementation Planning & Architecture Check | Draft technical implementation plan detailing component boundaries (app, modules, shared), Prisma data migrations, dependency injection, and constitution adherence checks. | .ai-context/plans/employee-internal-transfer.plan.md | D4 | Planned
7 | Thu 24 Sep 2026 |  | Task Breakdown & Test-First (TDD RED) | Decompose plan into atomic, independently verifiable tasks (T01-T15). Author executable automated tests in tests/backend/ and tests/frontend/ and confirm all tests fail RED before implementation. | .ai-context/tasks/employee-internal-transfer.tasks.md; tests/backend/*; tests/frontend/* (RED) | D5 | Planned
8 | Fri 25 Sep 2026 |  | Backend Implementation (GREEN) | Implement Express REST routes, validation middleware, transfer service, Prisma repositories, and integration adapters (HRMS, Payroll, IT IAM, Facilities). Verify backend unit & integration tests pass GREEN. | src/backend/app/*; src/backend/modules/transfer/*; src/backend/shared/* | D6 | Planned
9 | Sat 26 Sep 2026 |  | Frontend Implementation (GREEN) | Implement React + Vite + Tailwind UI components: employee IJP application form, 3-stage approval dashboard for managers/HR, status tracking view, and real-time state projection. Verify frontend tests pass GREEN. | src/frontend/app/*; src/frontend/modules/transfer/*; src/frontend/shared/* | D7 | Planned
10 | Mon 28 Sep 2026 |  | Gate 2 (Code Review) & Integration Verification | Execute full automated regression test suite, verify security checklist (PII-free logging, server-side auth, object-level checks). Submit for Gate 2 review by Technical Lead Supratim Jetty. | .ai-context/pr_reviews/gate-2-review.md; Test Suite Results (GREEN) | D8, D10 | Planned
11 | Tue 29 Sep 2026 |  | Release Packaging & Deployment Sign-off | Author formal release documentation, verify Definition of Done, update status board to Released (v1.0.0), and prepare deployment manifest. | .ai-context/releases/RELEASE-v1.0.0.md; .ai-context/status.md | D11 | Planned